## Sheet0
Jira.Project | Execution.Key | Execution.Assigned To | Execution.Executed By | Execution.Type | Execution.Execution Date | Execution.Actual | Execution.Estimated | Execution.Result | Execution.Environment | Execution.Linked Issues | Execution.Count of Linked Issues | Test Cycle.Key | Test Cycle.Name | Test Cycle.Description | Test Cycle.Folder | Test Cycle.Status | Test Cycle.Version | Test Cycle.Owner | Test Cycle.Planned Start Date | Test Cycle.Planned End Date | Test Case.Key | Test Case.Name | Test Case.Component | Test Case.Owner | Test Case.Created By | Test Case.Created On | Test Case.Version | Test Case.Estimated | Test Case.Objective | Test Case.Precondition | Test Case.Status | Test Case.Folder | Test Case.Labels | Test Case.Priority | Test Case.Traceability.Issue | Test Case.Traceability.Weblink
SCRUM | SCRUM-E1 | Sannan | Sannan | MANUAL | 2025-09-25 | 00:00 |  | Pass |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T1 | Validate booking a one-way trip |  | Sannan | Sannan | 2025-09-23 | 1 |  |  |  | Approved | /Booking a Flight/Flight Booking Valid Scenarios |  | High
SCRUM | SCRUM-E2 | Sannan | Sannan | MANUAL | 2025-10-01 | 00:00 |  | Blocked |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T2 | Validate booking a return trip |  | Sannan | Sannan | 2025-09-23 | 1 |  |  |  | Approved | /Booking a Flight/Flight Booking Valid Scenarios |  | High
SCRUM | SCRUM-E3 | Sannan | Sannan | MANUAL | 2025-10-01 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T10 | Validate booking when no departure date is selected |  | Sannan | Sannan | 2025-09-23 | 1 |  |  |  | Approved | /Booking a Flight/Flight Booking Valid Scenarios |  | High
SCRUM | SCRUM-E4 | Sannan | Sannan | MANUAL | 2025-10-01 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T9 | Validate booking when no destination is selected |  | Sannan | Sannan | 2025-09-23 | 1 |  |  |  | Approved | /Booking a Flight/Flight Booking Valid Scenarios |  | High
SCRUM | SCRUM-E5 | Sannan | Sannan | MANUAL | 2025-10-01 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T8 | Validate booking when no origin is selected |  | Sannan | Sannan | 2025-09-23 | 1 |  |  |  | Approved | /Booking a Flight/Flight Booking Valid Scenarios |  | High
SCRUM | SCRUM-E6 | Sannan | Sannan | MANUAL | 2025-10-01 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T4 | Validate booking when origin and destination are same |  | Sannan | Sannan | 2025-09-23 | 1 |  |  |  | Approved | /Booking a Flight/Flight Booking Valid Scenarios |  | High
SCRUM | SCRUM-E7 | Sannan | Sannan | MANUAL | 2025-10-01 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T7 | Validate booking when return date is before departure |  | Sannan | Sannan | 2025-09-23 | 1 |  |  |  | Approved | /Booking a Flight/Flight Booking Valid Scenarios |  | High
SCRUM | SCRUM-E8 | Sannan | Sannan | MANUAL | 2025-10-01 | 00:00 |  | Pass |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T3 | Validate booking with different origin and destination |  | Sannan | Sannan | 2025-09-23 | 1 |  |  |  | Approved | /Booking a Flight/Flight Booking Valid Scenarios |  | High
SCRUM | SCRUM-E9 | Sannan | Sannan | MANUAL | 2025-10-01 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T5 | Validate booking with future departure date |  | Sannan | Sannan | 2025-09-23 | 1 |  |  |  | Approved | /Booking a Flight/Flight Booking Valid Scenarios |  | High
SCRUM | SCRUM-E10 | Sannan | Sannan | MANUAL | 2025-10-01 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T6 | Validate booking with past departure date |  | Sannan | Sannan | 2025-09-23 | 1 |  |  |  | Approved | /Booking a Flight/Flight Booking Valid Scenarios |  | High
SCRUM | SCRUM-E11 | Sannan | Sannan | MANUAL | 2025-09-25 |  |  | Pass |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T27 | Validate leaving fields empty in passenger details. |  | Sannan | Sannan | 2025-09-25 | 1 |  |  |  | Draft | /Booking a Flight/Invalid passenger details |  | Normal
SCRUM | SCRUM-E12 | Sannan | Sannan | MANUAL | 2025-10-03 | 00:00 |  | Pass |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T29 | Validate payment with master card |  | Sannan | Sannan | 2025-09-25 | 1 |  |  |  | Draft | /Booking a Flight/Valid Payment |  | Normal
SCRUM | SCRUM-E13 | Sannan | Sannan | MANUAL | 2025-10-03 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T28 | Validate payment with visa card |  | Sannan | Sannan | 2025-09-25 | 1 |  |  |  | Draft | /Booking a Flight/Valid Payment |  | Normal
SCRUM | SCRUM-E14 | Sannan | Sannan | MANUAL | 2025-10-03 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T26 | Validate providing invalid information for passenger details "very long or numbers" |  | Sannan | Sannan | 2025-09-25 | 1 |  |  |  | Draft | /Booking a Flight/Invalid passenger details |  | Normal
SCRUM | SCRUM-E15 | Sannan | Sannan | MANUAL | 2025-10-03 | 00:00 |  | Pass |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T25 | Validate Providing valid information for pessenger details |  | Sannan | Sannan | 2025-09-23 | 1 |  |  |  | Draft | /Booking a Flight/Valid passenger details |  | Normal
SCRUM | SCRUM-E16 | Sannan | Sannan | MANUAL | 2025-10-01 | 00:00 |  | Pass |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T11 | Validate that booking a return trip is not allowed when the return date is before the departure date. |  | Sannan | Sannan | 2025-09-23 | 1 |  |  |  | Approved | /Booking a Flight/Flight Booking invalid Scenarios |  | Low
SCRUM | SCRUM-E17 | Sannan | Sannan | MANUAL | 2025-10-01 | 00:00 |  | Pass |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T22 | Validate that booking is not allowed when all fields are left empty. |  | Sannan | Sannan | 2025-09-23 | 1 |  |  |  | Approved | /Booking a Flight/Flight Booking invalid Scenarios |  | Low
SCRUM | SCRUM-E18 | Sannan | Sannan | MANUAL | 2025-10-01 | 00:00 |  | Pass |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T19 | Validate that booking is not allowed when no trip type is selected. |  | Sannan | Sannan | 2025-09-23 | 1 |  |  |  | Approved | /Booking a Flight/Flight Booking invalid Scenarios |  | Low
SCRUM | SCRUM-E19 | Sannan | Sannan | MANUAL | 2025-10-01 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T24 | Validate that booking is not allowed when only a return date is entered without a departure date. |  | Sannan | Sannan | 2025-09-23 | 1 |  |  |  | Approved | /Booking a Flight/Flight Booking invalid Scenarios |  | Low
SCRUM | SCRUM-E20 | Sannan | Sannan | MANUAL | 2025-10-01 | 00:00 |  | Pass |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T20 | Validate that booking is not allowed when selecting an invalid day or month (e.g., February 30). |  | Sannan | Sannan | 2025-09-23 | 1 |  |  |  | Approved | /Booking a Flight/Flight Booking invalid Scenarios |  | Low
SCRUM | SCRUM-E21 | Sannan | Sannan | MANUAL | 2025-10-03 | 00:00 |  | Pass |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T23 | Validate that booking is not allowed when special characters are entered in the city fields. |  | Sannan | Sannan | 2025-09-23 | 1 |  |  |  | Approved | /Booking a Flight/Flight Booking invalid Scenarios |  | Low
SCRUM | SCRUM-E22 | Sannan | Sannan | MANUAL | 2025-10-03 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T12 | Validate that booking is not allowed when the "From" field is empty. |  | Sannan | Sannan | 2025-09-23 | 1 |  |  |  | Approved | /Booking a Flight/Flight Booking invalid Scenarios |  | Low
SCRUM | SCRUM-E23 | Sannan | Sannan | MANUAL | 2025-10-03 | 00:00 |  | Blocked |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T13 | Validate that booking is not allowed when the "To" field is empty. |  | Sannan | Sannan | 2025-09-23 | 1 |  |  |  | Approved | /Booking a Flight/Flight Booking invalid Scenarios |  | Low
SCRUM | SCRUM-E24 | Sannan | Sannan | MANUAL | 2025-10-03 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T15 | Validate that booking is not allowed when the departure date is in the past. |  | Sannan | Sannan | 2025-09-23 | 1 |  |  |  | Approved | /Booking a Flight/Flight Booking invalid Scenarios |  | Low
SCRUM | SCRUM-E25 | Sannan | Sannan | MANUAL | 2025-10-03 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T14 | Validate that booking is not allowed when the origin and destination are the same. |  | Sannan | Sannan | 2025-09-23 | 1 |  |  |  | Approved | /Booking a Flight/Flight Booking invalid Scenarios |  | Low
SCRUM | SCRUM-E26 | Sannan | Sannan | MANUAL | 2025-10-03 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T16 | Validate that booking is not allowed when the return date is in the past. |  | Sannan | Sannan | 2025-09-23 | 1 |  |  |  | Approved | /Booking a Flight/Flight Booking invalid Scenarios |  | Low
SCRUM | SCRUM-E27 | Sannan | Sannan | MANUAL | 2025-10-03 | 00:00 |  | Not Executed |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T17 | Validate that booking is not allowed when the return date is the same as the departure date (if not supported). |  | Sannan | Sannan | 2025-09-23 | 1 |  |  |  | Approved | /Booking a Flight/Flight Booking invalid Scenarios |  | Low
SCRUM | SCRUM-E28 | Sannan | Sannan | MANUAL | 2025-10-03 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T21 | Validate that dropdowns do not allow typing invalid values. |  | Sannan | Sannan | 2025-09-23 | 1 |  |  |  | Approved | /Booking a Flight/Flight Booking invalid Scenarios |  | Low
SCRUM | SCRUM-E29 | Sannan | Sannan | MANUAL | 2025-10-03 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T42 | Validate that payment is not allowed when a valid Visa card number is entered but “Master” is selected as card type (and vice versa). |  | Sannan | Sannan | 2025-09-25 | 1 |  |  |  | Draft | /Booking a Flight/Invalid payment |  | Normal
SCRUM | SCRUM-E30 | Sannan | Sannan | MANUAL | 2025-10-03 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T40 | Validate that payment is not allowed when all fields are left empty. |  | Sannan | Sannan | 2025-09-25 | 1 |  |  |  | Draft | /Booking a Flight/Invalid payment |  | Normal
SCRUM | SCRUM-E31 | Sannan | Sannan | MANUAL | 2025-10-03 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T43 | Validate that payment is not allowed when expiry month entered is invalid (e.g., month 13 if dropdown allows). |  | Sannan | Sannan | 2025-09-25 | 1 |  |  |  | Draft | /Booking a Flight/Invalid payment |  | Normal
SCRUM | SCRUM-E32 | Sannan | Sannan | MANUAL | 2025-10-03 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T41 | Validate that payment is not allowed when invalid spaces are entered in the card number field. |  | Sannan | Sannan | 2025-09-25 | 1 |  |  |  | Draft | /Booking a Flight/Invalid payment |  | Normal
SCRUM | SCRUM-E33 | Sannan | Sannan | MANUAL | 2025-10-03 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T30 | Validate that payment is not allowed when no card type (Visa/Master) is selected. |  | Sannan | Sannan | 2025-09-25 | 1 |  |  |  | Draft | /Booking a Flight/Invalid payment |  | Normal
SCRUM | SCRUM-E34 | Sannan | Sannan | MANUAL | 2025-10-03 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T44 | Validate that payment is not allowed when pressing “Pay Now” without filling any field. |  | Sannan | Sannan | 2025-09-25 | 1 |  |  |  | Draft | /Booking a Flight/Invalid payment |  | Normal
SCRUM | SCRUM-E35 | Sannan | Sannan | MANUAL | 2025-10-03 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T36 | Validate that payment is not allowed when the card number contains alphabets or special characters. |  | Sannan | Sannan | 2025-09-25 | 1 |  |  |  | Draft | /Booking a Flight/Invalid payment |  | Normal
SCRUM | SCRUM-E36 | Sannan | Sannan | MANUAL | 2025-10-03 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T33 | Validate that payment is not allowed when the card number field is empty. |  | Sannan | Sannan | 2025-09-25 | 1 |  |  |  | Draft | /Booking a Flight/Invalid payment |  | Normal
SCRUM | SCRUM-E37 | Sannan | Sannan | MANUAL | 2025-10-03 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T34 | Validate that payment is not allowed when the card number has fewer digits than required. |  | Sannan | Sannan | 2025-09-25 | 1 |  |  |  | Draft | /Booking a Flight/Invalid payment |  | Normal
SCRUM | SCRUM-E38 | Sannan | Sannan | MANUAL | 2025-10-03 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T35 | Validate that payment is not allowed when the card number has more digits than required. |  | Sannan | Sannan | 2025-09-25 | 1 |  |  |  | Draft | /Booking a Flight/Invalid payment |  | Normal
SCRUM | SCRUM-E39 | Sannan | Sannan | MANUAL | 2025-10-03 | 00:00 |  | Fail |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T32 | Validate that payment is not allowed when the cardholder’s name contains numbers or special characters. |  | Sannan | Sannan | 2025-09-25 | 1 |  |  |  | Draft | /Booking a Flight/Invalid payment |  | Normal
SCRUM | SCRUM-E40 | Sannan | Sannan | MANUAL | 2025-10-03 | 00:00 |  | Pass |  |  | 0 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T31 | Validate that payment is not allowed when the cardholder’s name field is empty. |  | Sannan | Sannan | 2025-09-25 | 1 |  |  |  | Draft | /Booking a Flight/Invalid payment |  | Normal
SCRUM | SCRUM-E41 | Sannan | Sannan | MANUAL | 2025-10-01 | 00:00 |  | Fail |  | SCRUM-1 | 1 | SCRUM-R1 | Version 1.0 |  |  | In Progress |  | Sannan | 2025-09-25 | 2025-09-25 | SCRUM-T45 | Validate user can return to booking flight page to book another flight after successful payment |  | Sannan | Sannan | 2025-09-27 | 1 |  |  |  | Draft | /Booking a Flight/Valid Payment |  | Normal